## Main
Task No | Current Tasks in Queue. | Duration (in hours) | Status | Actual Time Spent
|  |  |  | Hour | Min
1 | Project Setup | 6 | Done | 6
2 | Login and Registration page update | 10 | Done | 10
3 | Change specification form to use fabtabolous | 24 | Done | 10
4 | Minor bugs | 4 | Done | 2
5 | Upload up to 5 files | 16 | Done | 2 | 30
6 | Popup with describing texts for all input fields | 8 | Done | 4
7 | Front page redesign | 16 | Done | 17
8 | New Design change Log | 4 | Done | 4
9 | Extra tasks and minor bugfixes | 5 | Done | 4 | 45
10 | Change Log till 30th January 09 | 12 | Done | 11 | 30
| Total Hours | 105 |  | 70 | 30
Date | Task Detail | Task No | Time Schedule
2008-12-30 | Project Setup | 1 | Sessions | Start Time | End Time | Total Hours
| Make proect up and running |  | Session 1 | 10:00 | 12:00 | 2
2008-12-31 | Project Setup | 1 | Sessions | Start Time | End Time | Total Hours
| Solving Error regarding database (some class files & jsp & tag files were missing and database configuration was not proper) |  | Session 1 | 10:00 | 15:00 | 4
2009-01-05 | Login and Registration page update | 2 | Sessions | Start Time | End Time | Total Hours
| Woking on design for login page and registration page |  | Session 1 | 9:30 | 12:30 | 3
2009-01-06 | Login and Registration page update | 2 | Sessions | Start Time | End Time | Total Hours
| Woking on design for login page and registration page |  | Session 1 | 10:30 | 13:00 | 2.5
| continue working on same task |  | Session 2 | 14:00 | 18:43 | 4.5
2009-01-07 | Front page redesign | 7 | Sessions | Start Time | End Time | Total Hours
| Woking on design for all pages in application |  | Session 1 | 9:30 | 13:00 | 3.5
| continue working on same task |  | Session 2 | 14:00 | 18:30 | 4.5
2009-01-08 | Front page redesign | 7 | Sessions | Start Time | End Time | Total Hours
| Woking on design for all pages in application |  | Session 1 | 9:10 | 13:00 | 4
| continue working on same task |  | Session 2 | 14:00 | 19:18 | 5.18
2009-01-09 | Popup with describing texts for all input fields | 6 | Sessions | Start Time | End Time | Total Hours
| Tooltip as a Javascript popup integration throughout the project |  | Session 1 | 9:10 | 13:00 | 4
| Discussion and understanding with designer for Fabtabulous and order page |  | Session 2 | 14:02 | 16:30 | 2.3
| Some Talleius Work along with little updation in Azitech |  | Session 3 | 16:30 | 18:50
2009-01-10 | New Design change Log | 8 | Sessions | Start Time | End Time | Total Hours
| New Design Integration throughout the application |  | Session 1 | 15:00 | 19:00 | 4
2009-01-12 | Change specification form to use fabtabolous | 3 | Sessions | Start Time | End Time | Total Hours
| Fabtabolous Integration |  | Session 1 | 9:15 | 13:00 | 4
| continue working on same task |  | Session 2 | 15:30 | 19:03 | 3.3
2009-01-13 | Change specification form to use fabtabolous | 3 | Sessions | Start Time | End Time | Total Hours
| Fabtabolous Integration |  | Session 1 | 9:02 | 10:35 | 2.3
| Multiple File Upload |  | Session 2 | 22:35 | 13:00 | 2.3
2009-01-16 | New Design change Log | 8 | Sessions | Start Time | End Time | Total Hours
| Change Log |  | Session 1 | 14:30 | 19:33 | 5
2009-01-17 | Order page Layout and Compatibility Issues among browsers |  | Sessions | Start Time | End Time | Total Hours
| Full Completion of Order page layout. Infobox change log. as well as Quotation page compatibility with all browser. |  | Session 1 | 9:05 | 12:00 | 3
2009-01-21 | Extra tasks and minor bugfixes |  | Sessions | Start Time | End Time | Total Hours
| Bugs |  | Session 1 | 10:30 | 13:00 | 2.3
2009-01-22 | Extra tasks and minor bugfixes |  | Sessions | Start Time | End Time | Total Hours
| Bugs |  | Session 1 | 15:30 | 5:45 | 2.15
2009-01-24 | Change Log till 30th January 09 |  | Sessions | Start Time | End Time | Total Hours
| Bugs |  | Session 1 | 15:30 | 18:30 | 3
2009-01-26 | Change Log till 30th January 09 |  | Sessions | Start Time | End Time | Total Hours
| Bugs |  | Session 1 | 9:00 | 12:50 | 4
2009-01-27 | Change Log 27th January 2009 |  | Sessions | Start Time | End Time | Total Hours
| Change Log |  | Session 1 | 15:15 | 16:45 | 1.3
2009-01-30 | Change Log 30th January 2009 |  | Sessions | Start Time | End Time | Total Hours
| Change Log |  | Session 1 | 15:45 | 18:45 | 3

## 3
Change specification form to use fabtabolous | Attachement
tabs.js
The specification form must be split into 3 subparts each showed in a tab. | livepipe.js
keyboard.js
We've previously used fabtabolous and we'll use it here again.
The basic idea of fabtabolous is to split a normal html page into a number of "pages" each shown in it's own tab.
The tabs are created as links linking to an anchored div. A link to <a href="#a"> displays the div with id="a":
<div >
<ul id="tab">
<li>
<a href="#a">Produkt / kategori</a>
</li> <li>
<a href="#b">Leverandør</a>
</li>
<li>
<a href="#c">Kontrol</a>
</li> <li>
<a href="#d">Temperatur</a>
</li> <li>
<a href="#e">Handling</a>
</li> </ul>
</div>
The pages to be shown are <div> tags each with it's own id and with class="panel". <div class="panel" id="a">
The things that should be in the first div is from the start until:
<div id="special" style="display: none">
<jsp:include page="special.jsp"/>
</div>
The next page should contain the next input fields until:
<div id="single" style="display: none">
<jsp:include page="single.jsp"/>
</div>
The last page should contain the gerberdata upload field and the submit button.
Next to the area with the form a textarea for comments should be shown.
Below the area with the pages a back and next button must be shown.
To control the next / back button code like this should probably be used:
<script>
document.observe('dom:loaded',function(){
var tab = new Control.Tabs('tab',{
afterChange: function(new_container){ }
}); $('tabnext').observe('click',function(event){
this.next(); Event.stop(event);
}.bindAsEventListener(tab));
});
</script>
<div class="tabnext">
<a href="" id="tabnext" style="margin-left:20px;">Næste</a>
</div>
I think we need extra javascript libraries:
<script src="${pageContext.request.contextPath}/ajax/keyboard.js" type="text/javascript"></script> <script src="${pageContext.request.contextPath}/ajax/livepipe.js" type="text/javascript"></script> <script src="${pageContext.request.contextPath}/ajax/tabs.js" type="text/javascript"></script>
These must be added to the right folder.

## 4
Minor bugs
On specification form:
Remove new button
Remove save button
Remove select box (choose existing specification)
For the specification form the input fields must be as small as possible without breaking existing design.
On quote page:
Replace: "Price per panel" with "Price per unit"
On Order page:
Remove verify order

## 5
Upload up to 5 files
Add 4 extra upload fields wherever the Gerberdata files can be uploaded. Implement fields in the Specification.java class. Right now we have one String property: gerberdata - we need 4 extra on top of that. In SpecificationActionBean? and OrderActionBean? we have the methods: saveGerberdata() and saveGerber(). These must be extended so that 5 files in total can be saved on the Specification Object.
This is a complex task, I would like to help you on that. Let me know if it gets too complex and I'll take over some of this.

## 6
Popup with describing texts for all input fields
We need a popup box for help texts for all input fields. So that mouseover over the label of the input field results in a popup showing some text.
For that we need a premade component that can work with the prototype javascript framework.

## 7
Front page redesign
The front page must be redesigned to make it look better and to make it fit into the iframe.
We split the page into 3 areas.
Top left ¦ Top right
Bottom
In the top left corner the links currently on the page must be placed. The look and feeling of the links must be improved so that they look better.
In the top right corner a box with a list of the titles of the specifications must be placed. (The list is already on the page). The box must be well formatted and probably fill 50% of the width.
In the bottom a list of orders (like now) must be placed.

## 9
Extra tasks and minor bugfixes
Main page:
| Set width on order list = 100%. | Y
| Show only the first 10 rows in Specifications table | Y
| Make the title be above the links (top-left corner) so that it doesn't cover the whole width. | Y
LOGIN page:
| Correct infobox text - remove "This is cool" | Y
| Add a link with text: "forgot password". (I'll add the functionality behind) - It's simple cut'n paste from another project | Y
(If it's easy add: "Remember me" and autologin checkboxes. (I haven't tried this before)
SPECIFICATION FORM PAGE:
| Add next / back buttons in the bottom. (One way of doing this is to put them inside the area that is changed on tab-change) | Y
| On Attachments the next button should replace "Place order". (Actually just change the text) | Y
| The dynamic javascript functionality doesn't work in internet explorer, please fix this. | Y
| The text: "Maximum value recommended" must only be shown if the value (see updateDim() ) is above 350. | Y
| On layout: If your own panel is chosen: "Your comments" textarea must be shown. (Moving it outside the area that is shown / hidden on panel type select box. | Y
QUOTE PAGE:
| The specification select box must be changed to be a hidden <stripes:hidden field and the title must be shown as plain text in the top. | Y
| Quantity (no of panels) must be changed so that the label = "Quantity" and the infobox contains: "Number of panels". | Y
| The values of the select box: Working days must be all numbers from 3-20. | Y

## 10
Change Log 24th October 2009
The committed stuff looks good. I have a few comments though 1) The back and next buttons in the specification form must change the active tab. 2) The front page design needs a final touch - the headline must have a right margin of around 5-10 pixels so that the underline doesn't go all the way into the specification form. 3) The rigth hand side of the specification table and order table on the frontpage must be aligned. And a few extra task, that I'm not sure I gave you: - The order page must be shined up, so that the labels and values are aligned. It would be nice if we can make it less high - one Idea is to make a layout where we have two label/value pairs per row like in the first 4 rows. label : value ¦ label : value - In the order page a print button must be added (top right corner). This should be possible to make using javascript.